## process
Payroll payment process
New system update/configuration
New activitivy
Current activity
| Current Process |  | To be process (Interim) |  | To be process (permanent)
Fin
|  | HR |  |  |  | (each entity)
(each entity)
Fin
(each entity)
HR
(each entity)
|  |  |  | HR |  | HR
|  |  |  | (each entity) |  | (each entity)
HR & Fin
(each entity)
|  |  |  | HR & Fin |  | HR & Fin
|  |  |  | (each entity) |  | (each entity)
[7 empty] | Host to Host: | one off cost (set up cost): USD5,000
|  | HR | [5 empty] | running cost: USD500/pm
(each entity)
|  |  |  | HR |  | HR
|  |  |  | (each entity) |  | (each entity)
|  | HR |  | HR |  | HR
|  | (each entity) |  | (each entity) |  | (each entity)
|  | Authorisers |  | Authorisers |  | Authorisers
|  | (each entity) |  | (each entity) |  | (each entity)
Download Payment report (.xls) in iHR system
(by employee, bank, currency)
& Check the payment data
Manual Upload in HSBCnet
(use the current HSBCnet profile)
Approve in HSBCnet
Set up new HSBCnet local profile for each VN entities (with openPGP encrypted)
Open bank account for salary (with linking to new HSBCnet local profile)
Run Reconciliation Report in iHRS system
& Check payment report vs payroll report
Down load Payment Report (.txt) from iHRIS with HSBC template (open PGP encrypted)
- without encryption
Download Payment report (.xls) in iHR system
(by employee, bank, currency)
& Check the payment data
Run Reconciliation Report in iHRS system
& Check payment report vs payroll report
Down load Payment Report (.txt) from iHRIS with HSBC template with encryption (open PGP encrypted)
Approve in HSBCnet
Manual Upload in HSBCnet
(use the current HSBCnet profile)
Approve in HSBCnet
Prepare Payroll and Download Payroll report (.xls) in iHRIS (local payroll system)
-Calculate the Payment data
-Create Payment Reports (.xls)
based on the payment rule
-Reconcile b/t Payroll and Payment report
Upgrade iHRIS (local payroll system) to cater for both Payroll report (as is) and Payment report (new)
Manually prepare HSBC upload template (non-encrypted)
(based on Payment report (.xls))
Approve Payroll Report and REconciliation report
(based on Payment report (.xls))
Upgrade iHRIS (local payroll system) to cater for both Payroll report (as is) and Payment report (new) and Encryption
Auto send the encrupted .txt payment file to HSBC folder
Decrupt the .txt file and upload to HSBCnet (new profile)
Manual Upload in HSBCnet the encrypted template
(into the new HSBCnet local profile)
Down load Payment Report (.txt) in iHRS (open PGP encrypted)
& Put .txt file in secured shared folder (with encrypted)

## timeline
| SoW for FPT to upgrade iHRS system |  |  |  | Engagement plan:
| - rule for payment |  |  | Binh/Mai | - Get confirmation/committment from FPT and HSBC on these timelines |  |  |  | done via meeting on 28/2/18. Timeline and process to be sent on 5/3/18
add | - download payment report in .xls template for checking |  |  | Binh/Mai | - Engage with Ricardo and Ms Duyen on the plan
| - download payment report in .txt template for uploading |  |  | Mai | - Engage with Regional Treasury on the solution (focus on new salary bank account) |  |  |  | endorsed by Jasmine on 28/2/18, now waiting for endorsement from Global treasury
add | - reconcile payroll and payment report
# | Actions for Interim solution | PIC | Timeline |  | # | Additional Actions for Permanent solution | PIC | Timeline
1 | PR, PO and Contract | Binh (IT) | 2018-02-13 |  | 1 | (i) Set up new HSBCnet profile with openPGP encrypted (ii) Test exchange keys PGP | HSBC (Thu/Vu) Mai (SMD) Huy (PMD) Ngoc (RO) FPT (Ngoc) | Mar'18 | - HSBC leadtime: 1 wk - create 3 HSBC local profile for 3 entities [1profile is only set for 1 VAT Code]
2 | FPT to upgrade the iHR system according to SoW | Binh (IT) Loan (RO & SMD TB) Ngoc (PMD) Thu (SMD JV) | 2018-03-27 |  | 2 | Open separate bank account for salary for SMD/RO or Map the existing salary bank account to new HSBCnet profile (PMD) | Mai (SMD) Huy (PMD) Ngoc (RO) | Mar'18 to May'18 | Approval time with Global treasury: 1-2 weeks BAM team: leadtime: 3 weeks
3 | Testing (SAT) -system and technical testing | Binh (IT) FPT HSBC | 2018-04-03 |  | 3 | SAT and UAT testing on new HSBCnet and new salary account and test on encrupted file | Binh (IT) Loan (RO & SMD TB) Ngoc (PMD) Thu (SMD JV) FPT HSBC | 1st week-Jun'18
4 | Come up Testing scenario (HR to also seek advice from HSBC) | Loan (RO & SMDTB) Ngoc (PMD) Thu (SMD JV) | 1st week Apr 18 |  | 4 | Penny testing in real system on new HSBCnet and new salary account | Binh (IT) Loan (RO & SMD TB) Ngoc (PMD) Thu (SMD JV) FPT HSBC | 2nd week-Jun'18
5 | UAT testing including training [1. testing scenarios in Payroll system] 2. scenarios from Payroll system, send file to HSBC] | Loan (RO & SMDTB) Ngoc (PMD) Thu (SMD JV) FPT HSBC | 2018-04-10 |  | 5 | Technical go live |  | Jun'18
6 | Penny testing in real system [HR come up testing volume + testing value] | Loan (RO & SMDTB) Ngoc (PMD) Thu (SMD JV) FPT HSBC | 2018-04-17 |  | 6 | Business go live (for Permanent solution) |  | Earlier July'18 payroll [- upload date: 23 July 18 - pay value date: 25 July 18]
7 | Technical go live |  | Apr'18
8 | Business go live (for Interim solution) |  | Earlier May'18 payroll [- upload date: 23 May 18 - pay value date: 25 May 18]
Justification for not live in Apr'18 payroll cycle:
- Bonus time which require a super care and many transactions